## Team & Setup
YOLOv8n Posit16 FPGA — 3-Person Team Plan
TEAM ROLES
Role | Person | Primary Responsibility | Skills Needed
Person A (RTL — LIGHTER LOAD) |  | Hybrid PE RTL modification Parameterized array generate loop Reduction tree scaling Timing closure support | SystemVerilog / Verilog Vivado synthesis Posit number format understanding
Person B (Software + PS) |  | PYNQ setup & driver code ARM NEON 1×1 conv kernel Posit16↔INT16 converter (C code) Frame capture + preprocessing NMS + post-processing Asyncio pipeline mAP benchmarking script | Python (PYNQ, numpy, OpenCV) C/C++ (ARM NEON intrinsics) Linux on Zynq PyTorch (for validation)
Person C (Integration + Vivado) |  | Vivado block design (AXI DMA, interconnect) Layer controller FSM (RTL or HLS) Im2col buffer Weight DMA double-buffering BRAM/URAM memory mapping Full system integration & debug | Vivado block design & IP integrator AXI protocol understanding FSM design (Verilog or HLS) Vivado ILA debug
DAY 0 — SETUP CHECKLIST (All 3 people, before Day 1)
Item | Owner | Details | Done?
Git repository | Any | Create shared repo with branches: rtl/, software/, integration/ | ☐
Vivado 2022.x installed | A + C | Same version on both machines. ZCU104 board files installed. | ☐
PYNQ SD image flashed | B | PYNQ v3.0.1 on ZCU104. SSH working. Jupyter accessible. | ☐
ZCU104 board working | B + C | Power on, UART console, HDMI passthrough test with base overlay. | ☐
PyTorch + Ultralytics | B | pip install ultralytics. Download yolov8n.pt. Run test inference on PC. | ☐
SoftPosit library | A | Build SoftPosit for x86 (validation) and ARM (optional PS use). | ☐
PDPU code imported | A | Current pdpu_code.zip unpacked in repo. Vivado sim project created. | ☐
COCO val2017 downloaded | B | 5000 images + annotations. On PC and copied to ZCU104 SD card. | ☐
Weight conversion script | B | Python: load yolov8n.pt → fold BN → convert FP32 → Posit16 → binary. | ☐
Camera / HDMI source | Any | USB webcam or HDMI camera available and tested with PYNQ base overlay. | ☐

## 25-Day Plan
25-DAY PROJECT PLAN — Task Assignments & Gantt Chart
# | Days | Task | Owner | Deliverable | Depends On | Risk | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
── PHASE 1: FOUNDATION ──
A1 | 1-3 | Hybrid PE: Replace Mitchell frac with DSP multiply | Person A | hybrid_posit_mult.sv passing 10K test vectors vs SoftPosit | Setup done | Med
B1 | 1-2 | Weight conversion: FP32→Posit16 (BN-folded) | Person B | Python script + binary weight files for all 75 layers | Setup done | Low
C1 | 1-3 | Vivado project: AXI DMA + AXI-Lite shell (empty accel) | Person C | Block design with DMA loopback test working on ZCU104 | Setup done | Low
B2 | 2-4 | PyTorch activation histogram @ 320×320 (regime cap validation) | Person B | Plot showing <0.1% activations outside [1/64, 64] | B1 | Low
A2 | 3-5 | Parameterized PE array (generate loop) + reduction tree | Person A | pdpu_array_banked.sv with N_BANKS, N_PES params. Sim passes. | A1 | Med
B3 | 3-5 | PYNQ setup + HDMI-In test + frame capture code | Person B | Python: capture 720p frame, resize to 320×320, save as numpy | C1 (board) | Low
C2 | 3-6 | Im2col hardware buffer (3×3 and 1×1 modes) | Person C | im2col_buffer.sv sim-verified against Python reference | None | Med
── PHASE 2: INTEGRATION (Days 6-12) ──
A3 | 5-7 | SiLU LUT: 256-entry Posit16 lookup table | Person A | silu_lut.sv + .hex file. Error < 0.5% vs PyTorch SiLU. | A1 | Low
C3 | 6-9 | Layer controller FSM (sequences all 3×3 conv layers) | Person C | layer_ctrl.sv: weight load → im2col → compute → writeback | A2, C2 | High
B4 | 5-8 | Posit16↔INT16 converter (C code + PL LUT module) | Person B | C function + posit16_to_int16.sv. Round-trip error < 1 LSB. | B2 | Med
B5 | 7-10 | ARM NEON 1×1 conv kernel (INT16 vectorized) | Person B | C function: neon_conv1x1_int16(). Benchmarked on ARM. | B4 | Med
C4 | 9-11 | Weight DMA double-buffer + BRAM address controller | Person C | Dual BRAM banks. DMA fills bank B while PL reads bank A. | C3 | Med
A4 | 7-9 | Tier 2 validation: 16-PE array on ZCU104 (synth+impl) | Person A | Post-impl resource report. 16 PEs @ ≥200 MHz confirmed. | A2, A3 | Med
── PHASE 3: FULL PIPELINE (Days 12-18) ──
C5 | 11-14 | Full backbone integration (P1-P5 conv layers on PL) | Person C | Single COCO image: backbone output matches PyTorch ±5% | C3, C4, A4 | High
B6 | 10-13 | PS pipeline: capture → resize → posit16 → DMA to PL | Person B | Python end-to-end: frame in → posit16 tensor in PL BRAM | B3, B4 | Med
A5 | 9-12 | Scale array to 128 PEs (8 banks × 16). Synth test. | Person A | Resource report: LUT <50%, DSP <10%, timing met. | A4 | Med
B7 | 13-16 | PS 1×1 conv + SiLU + residual add (all PS-side layers) | Person B | Python/C: full neck+head 1×1 path working on ARM | B5, B6 | Med
C6 | 14-17 | Neck + Head 3×3 layers + PS↔PL data exchange | Person C | Detection outputs in PS DRAM. Single image verified. | C5, B7 | High
A6 | 12-14 | Timing closure: 128 PEs @ 200 MHz (2-hop if needed) | Person A | Vivado impl passing timing. Bitstream generated. | A5 | Med
── PHASE 4: LIVE + BENCHMARK (Days 18-25) ──
B8 | 16-18 | NMS + bbox decode + OpenCV overlay on PS | Person B | Bounding boxes drawn on frame. Visual verification. | B7 | Low
C7 | 17-19 | Full system: asyncio frame pipeline (capture∥infer∥display) | Person C | Live detection loop running. FPS counter displayed. | C6, B8 | Med
A7 | 14-16 | ILA debug cores on array I/O (for debug support) | Person A | ILA probes on act_in, weight, result buses | A6 | Low
ALL | 19-21 | System debug + latency optimization | ALL 3 | Stable live detection. Measure per-layer latency. | C7 | Med
B9 | 21-24 | mAP benchmarking: 5-way comparison table | Person B | COCO val2017 (500+ imgs): FP32/FP16/INT8/P16/P16-DSP | C7 | Low
C8 | 21-23 | Power + resource measurement (Vivado reports) | Person C | Utilization table, power analysis, clock frequency | C7 | Low
A8 | 16-18 | RTL cleanup + documentation + testbench final | Person A | All .sv files documented. Testbenches pass. Git tagged. | A7 | Low
ALL | 24-25 | Results write-up + demo video recording | ALL 3 | Paper tables, architecture diagram, live demo video | B9, C8 | Low

## Person A — RTL
Person A — RTL (Lighter Load: ~60% utilization)
Total RTL work: ~400-500 new/modified lines of SystemVerilog. Rest of time: synthesis runs + debug support.
Task ID | Task | Detailed Steps | Files to Create/Modify
A1 Days 1-3 | Hybrid PE multiply | 1. Copy pdpu_mitchell_mult.v → hybrid_posit_mult.sv 2. KEEP lines 1-93 (decode logic) exactly as-is 3. DELETE lines 94-130 (Mitchell frac approx + LUT) 4. REPLACE with: assign frac_product = frac_a * frac_b; (Vivado infers DSP48E2 from 11×11 multiply) 5. Add frac_product normalization (overflow check) 6. KEEP encode logic (lines 131-180) with adjusted frac input 7. Run testbench with 10,000 random Posit16 pairs 8. Compare against SoftPosit: MRE should be <0.1% (better than Mitchell) | NEW: hybrid_posit_mult.sv (~180 lines) MODIFY: posit_defines.svh (remove Mitchell LUT refs) DELETE: mitchell_corr_lut.hex (no longer needed) NEW: tb_hybrid_mult.sv (~100 lines)
A2 Days 3-5 | Parameterized array | 1. Copy pdpu_array.sv → pdpu_array_banked.sv 2. Replace 4 hand-instantiated PEs with generate loop 3. Add N_BANKS parameter (default 1 for initial test) 4. Replace reduction tree with parameterized version (log2 depth, use generate for binary tree) 5. Sim with N_BANKS=1, N_PES=4 — must match old results 6. Sim with N_BANKS=1, N_PES=16 — verify scaling | NEW: pdpu_array_banked.sv (~120 lines) MODIFY: pdpu_reduction_tree.sv (parameterize) MODIFY: pdpu_pe.sv (use hybrid_posit_mult) NEW: tb_array_banked.sv (~150 lines)
A3 Days 5-7 | SiLU LUT | 1. Python script: generate 256-entry Posit16 SiLU table Input: Posit16 values spanning activation range Output: SiLU(x) in Posit16 2. Export as .hex file 3. RTL: simple ROM lookup (8-bit address from top bits) 4. Validate error vs PyTorch SiLU on 10K test values | NEW: silu_lut.sv (~40 lines) NEW: silu_lut.hex (256 entries) NEW: gen_silu_lut.py (~30 lines)
A4 Days 7-9 | Tier 2 synthesis (16 PEs) | 1. Set N_BANKS=1, N_PES=16 in defines 2. Wrap in AXI-Lite slave (C provides template) 3. Run Vivado synthesis + implementation 4. Check: LUT, DSP, BRAM, Fmax 5. Fix any timing violations → This is mostly WAITING for Vivado runs | MODIFY: posit_defines.svh Vivado project (shared with C)
A5 Days 9-12 | Scale to 128 PEs (8×16) | 1. Set N_BANKS=8, N_PES=16 2. Synthesize — expect ~40% LUT, ~7% DSP 3. If timing fails: add pipeline register stage in PE 4. May need 2-hop activation delay (add act_pipe2_r) | MODIFY: posit_defines.svh Possibly MODIFY: pdpu_pe.sv (add pipeline stage)
A6 Days 12-14 | Timing closure 200 MHz | 1. Run full implementation with timing constraints 2. Analyze critical paths (Vivado timing report) 3. If failing: insert register stages at identified paths 4. Re-run until timing met → Mostly Vivado run time + targeted fixes | Vivado constraints file (.xdc) Minor RTL pipeline fixes if needed
A7 Days 14-16 | ILA debug cores | 1. Add ILA probes on: arr_act_in, arr_weights[0], arr_result 2. Add ILA on DMA handshake signals 3. Resynthesize with ILA → Support C during system debug | Vivado ILA insertion (GUI or Tcl)
A8 Days 16-18 | Cleanup + documentation | 1. Add module-level comments to all .sv files 2. Verify all testbenches pass clean 3. Write RTL section of paper (architecture description) 4. Git tag final RTL version | All .sv files (comments) README.md for RTL

## Person B — Software
Person B — Software + PS (Heaviest load: ~90% utilization)
Task ID | Task | Detailed Steps | Files to Create
B1 Days 1-2 | Weight conversion script | 1. Load yolov8n.pt with Ultralytics 2. Iterate all Conv2d layers: fold BN weights w_fold = w * (gamma / sqrt(var + eps)) b_fold = beta + (bias - mean) * gamma / sqrt(var+eps) 3. Convert FP32 → Posit16 (use softposit or custom) 4. Export per-layer binary files: layer_00_weights.bin, layer_00_bias.bin 5. Also export layer config JSON: {kernel:3, cin:16, cout:32, stride:2, ...} 6. Verify: reload and compare vs PyTorch output | weight_convert.py layer_config.json weights/ directory posit16_utils.py
B2 Days 2-4 | Activation histogram + regime validation | 1. Run YOLOv8n inference on 100 COCO images @ 320×320 2. Hook every layer output, record histograms 3. Convert activations to Posit16, count regime saturation 4. Plot: activation distribution per layer 5. Confirm <0.1% exceed [1/64, 64] range 6. Generate golden test vectors for A's testbenches | regime_validation.py activation_histograms.pdf golden_vectors/ directory
B3 Days 3-5 | PYNQ setup + frame capture | 1. Flash PYNQ v3.0.1 on ZCU104 SD card 2. Boot, verify Jupyter accessible 3. Test base overlay HDMI-In passthrough 4. Write Python: capture frame → numpy array 5. Add resize to 320×320 (cv2.resize) 6. Measure capture + resize latency | notebooks/test_hdmi.ipynb capture.py
B4 Days 5-8 | Posit16 ↔ INT16 converter | 1. Python reference: posit16_to_int16() and reverse Strategy: decode posit → fixed-point scaling INT16 = round(posit_value * 2^FRAC_BITS) Choose FRAC_BITS=10 (covers [-32, 31.999]) 2. C implementation for ARM (will be called from NEON) 3. Measure round-trip error on activation distributions 4. Also provide: posit16_to_int16.sv for PL boundary (send to A for integration) | posit16_int16.py (reference) posit16_int16.c (ARM) posit16_to_int16.sv (for Person A)
B5 Days 7-10 | ARM NEON 1×1 conv kernel | 1. Write C function with NEON intrinsics: void neon_conv1x1_int16( int16_t* input, // [H*W, Cin] int16_t* weight, // [Cout, Cin] int16_t* output, // [H*W, Cout] int H, int W, int Cin, int Cout) 2. Use vmlal_s16 for 8-wide MAC 3. Process 4 output channels per core (OpenMP) 4. Benchmark: measure GOPS on ZCU104 ARM 5. Validate output vs PyTorch 1×1 conv | neon_conv1x1.c neon_conv1x1.h test_neon_conv.py
B6 Days 10-13 | End-to-end PS input pipeline | 1. Capture frame → resize 320×320 2. Normalize pixels to [0, 1] 3. Convert FP32 → Posit16 (numpy vectorized) 4. Allocate PYNQ contiguous buffer 5. DMA transfer Posit16 tensor to PL 6. Measure full pipeline latency | ps_pipeline.py dma_utils.py
B7 Days 13-16 | Full PS-side layer processing | 1. Integrate neon_conv1x1 for all 1×1 conv layers 2. Add SiLU activation (either LUT array or math.h) 3. Add residual add (element-wise Posit16 add or INT16) 4. Add SPPF maxpool (simple comparison loop) 5. Add upsample (nearest-neighbor index duplication) 6. Sequence: receive PL output → PS layers → send to PL | ps_layers.py (or .c compiled as .so) layer_scheduler.py
B8 Days 16-18 | NMS + display overlay | 1. Posit16 → FP32 conversion for head outputs 2. Sigmoid on class scores 3. DFL box decoding 4. NMS (cv2.dnn.NMSBoxes or custom) 5. Draw bounding boxes on frame (OpenCV) 6. Display via DisplayPort or HDMI-Out | postprocess.py display.py
B9 Days 21-24 | mAP benchmarking | 1. Run full inference on 500+ COCO val2017 images 2. Save predictions in COCO JSON format 3. Evaluate with pycocotools 4. Generate 5-way table: FP32 (PyTorch CPU) / FP16 / INT8 / Posit16 / P16-DSP 5. Record FPS for each run 6. Plot accuracy vs precision comparison | benchmark.py results_table.xlsx accuracy_comparison.pdf

## Person C — Integration
Person C — Integration + Vivado (Heaviest complexity: system-level debug)
Task ID | Task | Detailed Steps | Files to Create
C1 Days 1-3 | Vivado block design shell | 1. Create Vivado project targeting XCZU7EV 2. Block design: Zynq PS → AXI interconnect 3. Add AXI DMA (MM2S + S2MM channels) 4. Add AXI-Lite slave for accelerator control regs 5. Add placeholder RTL module (pass-through) 6. Generate bitstream, test DMA loopback on ZCU104 7. Verify with PYNQ: allocate → DMA send → receive → compare | vivado/block_design.tcl vivado/constraints.xdc test_dma_loopback.py
C2 Days 3-6 | Im2col hardware buffer | 1. Design im2col_buffer.sv: Inputs: base_addr, kernel_size(1 or 3), H, W, Cin, stride Output: flat Posit16 vector (9*Cin or 1*Cin elements) 2. Address generator: nested loop over output pixels 3. Zero-padding logic for border pixels 4. Interface: AXI-Stream out to PDPU array 5. Testbench: compare vs Python im2col on known feature map | im2col_buffer.sv (~200 lines) tb_im2col.sv im2col_reference.py
C3 Days 6-9 | Layer controller FSM | 1. FSM states: IDLE → LOAD_WEIGHTS → CONFIGURE_IM2COL → COMPUTE → WRITE_OUTPUT → NEXT_LAYER → DONE 2. For each output channel: a. Load N_PES weights from weight BRAM b. For each output pixel: im2col → stream through array c. Collect reduction tree output → write to output BRAM 3. Layer config via AXI-Lite registers: kernel_size, Cin, Cout, H_in, W_in, stride 4. PS writes config, sets START bit, waits for DONE interrupt | layer_ctrl.sv (~300 lines) axi_lite_regs.sv (~100 lines) tb_layer_ctrl.sv
C4 Days 9-11 | Weight DMA double-buffer | 1. Two weight BRAM banks (A and B) 2. Ping-pong controller: While PL reads from bank A → DMA fills bank B On layer boundary: swap 3. PS driver: pre-schedule next layer weights via DMA 4. Handshake: layer_ctrl signals "weights consumed" → DMA controller starts next fill | weight_dma_ctrl.sv (~100 lines) MODIFY: layer_ctrl.sv (add bank swap logic)
C5 Days 11-14 | Full backbone integration | 1. Connect: im2col → PDPU array → SiLU → output BRAM 2. Configure layer_ctrl for all backbone 3×3 conv layers 3. PS driver: iterate layers, set config regs, trigger compute 4. Test: single COCO image through backbone 5. Compare P3/P4/P5 feature maps vs PyTorch ±5% 6. Debug with ILA if mismatch (coordinate with A) | MODIFY: block design (full integration) backbone_test.py
C6 Days 14-17 | Neck + Head + PS↔PL data exchange | 1. Add PS↔PL synchronization for layer dispatch: PL does 3×3 conv → signals PS → PS does 1×1 conv → PS signals PL → PL does next 3×3 2. Shared DRAM buffers for feature map exchange 3. Add interrupt handling in PYNQ driver 4. Test full pipeline: single image → detection output | MODIFY: layer_ctrl.sv (add PS sync) MODIFY: block design full_pipeline_test.py
C7 Days 17-19 | Asyncio frame pipeline | 1. Integrate B's capture + preprocessing 2. Integrate B's NMS + display 3. Build asyncio loop: Task 1: capture frame N (async DMA) Task 2: infer frame N-1 (PL compute + PS layers) Task 3: display frame N-2 (OpenCV overlay) 4. Add FPS counter 5. Optimize: tune DMA burst size, buffer count | live_detect.py MODIFY: dma_utils.py
C8 Days 21-23 | Resource + power measurement | 1. Vivado utilization report (post-implementation) 2. Vivado power analysis (switching activity) 3. Tabulate: LUT, FF, DSP, BRAM, URAM, Fmax, Power 4. Compare vs INT8 baselines from literature | resource_table.xlsx power_report.pdf

## Dependencies
Task Dependencies & Critical Path
From Task | Description | To Task | Description | Handoff Item
A1 | Hybrid PE multiply done | A2 | Parameterized array | hybrid_posit_mult.sv
A2 | Array parameterized | C3 | Layer controller FSM | pdpu_array_banked.sv
A2 | Array parameterized | A4 | Tier 2 synthesis | Synthesis-ready RTL
A4 | Tier 2 resource report | A5 | Scale to 128 PEs | Resource headroom confirmed
B1 | Weights converted | B2 | Activation histogram | Posit16 weight files
B2 | Golden vectors generated | A1 | Hybrid PE testbench | golden_vectors/*.bin
B4 | Posit16↔INT16 converter | B5 | NEON 1×1 conv | posit16_int16.c
B4 | PL converter module | C6 | PS↔PL data exchange | posit16_to_int16.sv
C1 | DMA shell working | B3 | PYNQ frame capture | Working bitstream + overlay
C2 | Im2col buffer done | C3 | Layer controller FSM | im2col_buffer.sv
C3 | Layer FSM done | C4 | DMA double-buffer | layer_ctrl.sv
C3+C4 | Layer ctrl + DMA | C5 | Backbone integration | Full PL compute path
A5 | 128-PE synthesis | A6 | Timing closure | Synthesis results
A6 | Bitstream ready | C5 | Backbone test on board | posit_yolov8.bit
C5 | Backbone verified | C6 | Full pipeline | Backbone passing on HW
B7 | PS layers working | C6 | Full pipeline | PS-side compute ready
C6 | Full pipeline working | C7 | Live frame loop | Single-image inference OK
C7 | Live detection running | B9 | mAP benchmarking | Stable system
CRITICAL PATH (longest dependency chain — determines project end date):
A1 → A2 → C3 → C4 → C5 → C6 → C7 → B9 → Write-up
Days: 1-3 → 3-5 → 6-9 → 9-11 → 11-14 → 14-17 → 17-19 → 21-24 → 24-25 (Person C is on the critical path most of the time)

## Daily Sync
Daily Standup Protocol (15 min max)
When | Every morning, 15 minutes. Non-negotiable.
Format | Each person: (1) What I finished yesterday (2) What I'm doing today (3) Am I blocked?
BLOCKING RULES | Action | Prevention
A blocks C | A's RTL module not ready for C's integration | A provides stub/interface file on Day 1 so C can develop against it
B blocks C | B's PYNQ/DMA code not ready for system test | C tests with PYNQ DMA loopback first (C1 task)
C blocks B | C's bitstream not ready for B to test PS pipeline | B develops and tests PS code on PC with PyTorch reference first
Vivado blocks all | Synthesis takes 2-4 hours, impl takes 4-8 hours | Launch synthesis overnight. Never wait for Vivado during work hours.
GIT PROTOCOL
Branches | main (stable), rtl/dev (A), software/dev (B), integration/dev (C)
Merge rule | Only merge to main when feature is sim-verified or board-tested
Commit message | [A/B/C] Task-ID: description. Example: [A] A1: hybrid mult passing 10K vectors
HANDOFF PROTOCOL
RTL → Integration | A pushes to rtl/dev. C pulls and integrates. A provides interface doc in README.
Software → Board | B tests on PC first. Then tests on ZCU104 with base overlay. Then tests with custom overlay.
Files → Board | B maintains weights/ and config/ directories on ZCU104 SD card via SCP.